## Q1.Dashboard_Cum_Schedule
Name:Rajeev Raghu Raman Arunachalam | Current Designation/ Role @ CapGemini: Manager - Delivery Manager cum Scrum Master
Activity[Roles] | Schedule |  | Duration(Hours) | Status | 2018-10-15 | 2018-10-16 | 2018-10-17 | 2018-10-18 | 2018-10-19 | 2018-10-20 | 2018-10-21 | 2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-25 | 2018-10-26 | 2018-10-27 | 2018-10-28 | 2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28 | 2018-11-29 | 2018-11-30 | 2018-12-01 | 2018-12-02 | 2018-12-03 | 2018-12-04 | 2018-12-05 | 2018-12-06 | 2018-12-07 | 2018-12-08 | 2018-12-09 | 2018-12-10 | 2018-12-11 | 2018-12-12 | 2018-12-13 | 2018-12-14 | 2018-12-15 | 2018-12-16 | 2018-12-17 | 2018-12-18 | 2018-12-19 | 2018-12-20 | 2018-12-21 | 2018-12-22 | 2018-12-23 | 2018-12-24 | 2018-12-25 | 2018-12-26 | 2018-12-27 | 2018-12-28 | 2019-12-29 | 2019-12-30
| Start Date | End Date
Requirements [Analyst] |  |  | 256
Onsite Visit | 2018-10-15 | 2018-10-17 | 24
Elicit requirements | 2018-10-18 | 2018-10-20 | 24
Drawing wireframes | 2018-10-21 | 2018-10-25 | 40
Documenting Requirements | 2018-10-26 | 2018-10-29 | 32
Use Case diagram | 2018-10-30 | 2018-11-05 | 56
Requirement Approval and Freezing(Including modifications) | 2018-11-06 | 2018-11-09 | 32
Project Management Activities[Project Manager] | Ongoing | Ongoing | 48
Design[Software Developer] |  |  | 128
Technology Usage freezing | 2018-11-10 | 2018-11-12 | 24
Module split | 2018-11-13 | 2018-02-18 | 48
Workflow design | 2018-11-19 | 2018-11-22 | 32
Project Management Activities[Project Manager] | Ongoing | Ongoing | 24
Implementation[Software Developer] |  |  | 168
Component or Module design | 2018-11-23 | 2018-11-28 | 48
Component Unit testing(Test - Design & Execution) | 2019-11-29 | 2018-12-03 | 40
System integration design | 2018-12-04 | 2018-12-06 | 24
System Integration unit test | 2018-12-07 | 2018-12-10 | 32
Project Management Activities[Project Manager] | Ongoing | Ongoing | 24
Testing[Software Tester] |  |  | 80
Component Testing | 2018-12-11 | 2018-12-13 | 24
System Integration Testing | 2018-12-14 | 2018-12-15 | 16
Security & Performance Testing | 2018-12-16 | 2018-12-17 | 16
Project Management Activities[Project Manager] | Ongoing | Ongoing | 24
Deployment[Software Release Team member] |  |  | 56
Onsite Visit | 2018-12-18 | 2018-12-19 | 16
Environment Setup | 2018-12-20 | 2018-12-20 | 8
Deploy into Production system | 2018-12-21 | 2018-12-21 | 8
Project Management Activities[Project Manager] | Ongoing | Ongoing | 24
Maintenance[Software Maintenance Team member] |  |  | 96
Handle change requests - Feature (Bi annual) | 2018-12-22 | 2018-12-23 | 16
Change control board process | 2018-12-24 | 2018-12-24 | 8
Monitor Production | 2018-12-25 | 2018-12-28 | 32
Signoff | 2028-12-29 | 2018-12-29 | 8
Project Management Activities[Project Manager] | Ongoing | Ongoing | 32
Assumptions
Assuming 1 (BA)associates for requirement elicitation
Assuming 1 project manager
Assuming 1 Tester,Developer,Analyst
Assuming 1 associate - 8 hrs work per day
For simplicity weekends and holidays not considered
Analyst Activity - Requirements phase
Project Management Activity
Software developer activity-Design phase
Software developer activity-Implementation phase
Software Tester activity - Testing Phase
Software release activity - Deployment phase
Software maintenance activity - Maintenance phase

## Q2.Cost_Estimation
Name: Rajeev Raghu Raman Arunachalam
Project Phase | Estimated Hours | Analyst |  | Developer |  | Tester |  | Release member |  | Maintenance member |  | Project Manager
|  | Requirement | Cost | Requirement | Cost | Requirement | Cost | Requirement | Cost | Requirement | Cost | Requirement | Cost | Total Phase Cost
Requirements [Analyst] | 256 |  | 2560 | [10 empty] | 4000
Onsite Visit | 24 | 1 | 240 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Elicit requirements | 24 | 1 | 240 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Drawing wireframes | 40 | 1 | 400 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Documenting Requirements | 32 | 1 | 320 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Use Case diagram | 56 | 1 | 560 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Requirement Approval and Freezing(Including modifications) | 32 | 1 | 320 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Project Management Activities[Project Manager] | 48 | 1 | 480 | NA | NA | NA | NA | NA | NA | NA | NA | 1 | 1440
Design[Software Developer] | 128 |  |  |  | 2080 | [8 empty] | 2800
Technology Usage freezing | 24 | NA | NA | 1 | 480 | NA | NA | NA | NA | NA | NA | NA | NA
Module split | 48 | NA | NA | 1 | 960 | NA | NA | NA | NA | NA | NA | NA | NA
Workflow design | 32 | NA | NA | 1 | 640 | NA | NA | NA | NA | NA | NA | NA | NA
Project Management Activities[Project Manager] | 24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 1 | 720
Implementation[Software Developer] | 168 |  |  |  | 2880 | [8 empty] | 3600
Component or Module design | 48 | NA | NA | 1 | 960 | NA | NA | NA | NA | NA | NA | NA | NA
Component Unit testing(Test - Design & Execution) | 40 | NA | NA | 1 | 800 | NA | NA | NA | NA | NA | NA | NA | NA
System integration design | 24 | NA | NA | 1 | 480 | NA | NA | NA | NA | NA | NA | NA | NA
System Integration unit test | 32 | NA | NA | 1 | 640 | NA | NA | NA | NA | NA | NA | NA | NA
Project Management Activities[Project Manager] | 24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 1 | 720
Testing[Software Tester] | 80 | [5 empty] | 560 | [6 empty] | 1280
Component Testing | 24 | NA | NA | NA | NA | 1 | 240 | NA | NA | NA | NA | NA | NA
System Integration Testing | 16 | NA | NA | NA | NA | 1 | 160 | NA | NA | NA | NA | NA | NA
Security & Performance Testing | 16 | NA | NA | NA | NA | 1 | 160 | NA | NA | NA | NA | NA | NA
Project Management Activities[Project Manager] | 24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 1 | 720
Deployment[Software Release Team member] | 56 | [7 empty] | 320 |  |  |  |  | 1040
Onsite Visit | 16 | NA | NA | NA | NA | NA | NA | 1 | 160 | NA | NA | NA | NA
Environment Setup | 8 | NA | NA | NA | NA | NA | NA | 1 | 80 | NA | NA | NA | NA
Deploy into Production system | 8 | NA | NA | NA | NA | NA | NA | 1 | 80 | NA | NA | NA | NA
Project Management Activities[Project Manager] | 24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 1 | 720
Maintenance[Software Maintenance Team member] | 96 | [9 empty] | 736 |  |  | 1696
Handle change requests - Feature (Bi annual) | 16 | NA | NA | NA | NA | NA | NA | NA | NA | 1 | 240 | NA | NA
Change control board process | 8 | NA | NA | NA | NA | NA | NA | NA | NA | 1 | 120 | NA | NA
Monitor Production | 32 | NA | NA | NA | NA | NA | NA | NA | NA | 1 | 256 | NA | NA
Signoff | 8 | NA | NA | NA | NA | NA | NA | NA | NA | 1 | 120 | NA | NA
Project Management Activities[Project Manager] | 32 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 1 | 960
Grand Total | 784 |  | 2560 |  | 4960 |  | 560 |  | 320 |  | 736 |  | 5280 | 14416
Summary
Total FTE | 6
Total Estimated Effort | 784
Total Estimated Cost | 14416$
Assumptions
Assuming 1 (BA)associates for requirement elicitation
Assuming 1 project manager
Assuming 1 Tester,Developer,Analyst
Assuming 1 associate - 8 hrs work per day
For simplicity weekends and holidays not considered
I assume time & material hourly billing system
Analyst- 10$/hour
Developer - 20$/hour
Tester-10$/hour
Release-10$/hour
Maintenance-15$/hour
Project Manager-30 $/hour
NA-> Not Applicable
Sub Total Cost-Role
Overall Total Phase cost
Overall Project Cost estimation
FTE-> Full Time Employee
Instructions To Team
1 | Team is to fill their Time Sheets on a daily basis
2 | Track any outages like network issues and other downtimes relating to non productive hours with due comments
3 | Then send the daily report sheet to me so that I can monitor/track costs.